## Sheet1
TimeLine
Aktivitas | Sub Aktivitas | Detail | APRIL | [9 empty] | MEI
|  |  | week 12 |  |  |  | week 13 | [5 empty] | week 14 | [5 empty] | week 15 | [5 empty] | week 16
|  |  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Persiapan | Pemilihan Kasus dan Algoritma | Pemilihan Kasus | bar: week 12 21 to week 12 24
Penentuan Algoritma | bar: week 12 23 to week 13 25
Pelaksanaan | Business Understanding | Menentukan Objektif Bisnis | bar: week 12 23 to week 13 26
Menentukan Tujuan Bisnis | bar: week 12 24 to week 13 26
| Data Understanding | Menentukan Data yang akan dianalisi menggunakan sentimen analisis | bar: week 13 26 to week 13 27
Menelaah Data tweet musik | bar: week 13 26 to week 13 28
Memvalidasi Data | bar: week 13 26 to week 13 28
| Data Preparation | Memilih Data | bar: week 13 28 to week 15 9
Membersihkan Data | bar: week 13 28 to week 15 9
Mengkonstruksi Data | bar: week 13 28 to week 15 9
Menentukan Label Data | bar: week 13 28 to week 15 9
Mengintegrasikan Data | bar: week 13 28 to week 15 9
| Modeling | Membangun Skenario Pengujian | bar: week 13 30 to week 16 13
Membangun Model | bar: week 13 30 to week 16 13
| Model Evaluation | Mengevaluasi Hasil Pemodelan | bar: week 13 30 to week 16 13
Melakukan Review Proses Pemodelan | bar: week 14 4 to week 16 13
| Deployment | Melakukan Deployment Model | bar: week 14 4 to week 16 13
Membuat Laporan Akhir Proyek | bar: week 15 10 to week 16 15